## Risks
# | Risks | severity | Priority | Likelihood | RPN | Key
5 a) | UE isn't able to place inbound/outbound calls net-net, net-pstn, net-comcast, net-sprint | 1 | 1 | 1 | 1 | severity
5 b) | UE doesn't get to emergency services | 1 | 1 | 1 | 1 | 1 loss of data, hardware damage or a saftey issue
11 | Media not handled by SBC as expected (NAT traversal on Access/Interconnect) | 1 | 1 | 1 | 1 | 2 loss of functionality with no workaround
3 b) | replication of data between SBC's | 2 | 1 | 1 | 2 | 3 loss of functionality with a workaround
3 c) | replication of config between SBC's | 2 | 1 | 1 | 2 | 4 partial loss of functionality
3 d) | backed up configs can't be used | 2 | 1 | 1 | 2 | 5 cosmetic or trivial
4 b) | SIP routing doesn't route the calls | 2 | 1 | 1 | 2
9 | TLS or Ipsec doesn't allow setup for signalling | 1 | 2 | 1 | 2 | priority
22 | SBC is unable to bind a given UE to a given Porxy through the course of a registration | 2 | 1 | 1 | 2 | 1 complete loss of system value
3 a) | virtual IP's don't move over in a fail over | 2 | 1 | 2 | 4 | 2 unacceptable loss of system value
15 | SBC and P-CSCF can't distinguish signalling between multiple end points | 2 | 2 | 1 | 4 | 3 possibly acceptable reduction in system value
16 | BGF is not provided destination for incoming media | 2 | 2 | 1 | 4 | 4 acceptable reduction in system value
19 | DTMF isn't handled correctly | 2 | 2 | 1 | 4 | 5 negligible reduction in system value
21 | SBC is unable to resolve hostname to IP | 2 | 2 | 1 | 4
4 | config has been FTP'd incorrectly | 1 | 2 | 4 | 6 | likelihood
4 a) | inlicensed feature in config (saved on one SBC and moved to a second SBC with different licenses | 1 | 2 | 4 | 6 | 1 certain to affect all users
8 | CDR's don't report correctly (? Radius vs. FTP Push) | 1 | 2 | 3 | 6 | 2 likely to impact some users
17 | SBC doesn't terminate call after UE loses connectivity | 3 | 3 | 1 | 6 | 3 possible impact on some users
2 | Ethernet port fail at layer 2 | 2 | 2 | 2 | 8 | 4 limited impact to few users
3 | HA event doesn't handle IP's Correctly | 2 | 2 | 2 | 8 | 5 unimaginable in actual usage
5 | SIP message doesn't arrive in the expected formate (HMR) | 2 | 2 | 2 | 8
7 | Radius Auth doesn't allow authentication | 2 | 2 | 2 | 8
13 | HDR doesn't interact with T-PIM or provides incorrect/unusable data | 1 | 2 | 4 | 8
14 | Interruption of the HDR causes unexceptable loss of data | 1 | 2 | 4 | 8
18 | SBC doesn't handle switched services (CW, hold, 3-way) | 2 | 2 | 2 | 8
6 | SNMP poll return bad data | 2 | 2 | 3 | 12
10 | Collection push errors | 1 | 3 | 4 | 12
12 | CALEA doesn't interact with Star Gate correctly | 2 | 2 | 4 | 16
20 | Headers that describe priv network are passed to UE/Peers | 2 | 2 | 4 | 16
23 | Call stood up fails during a config change/upgrade | 2 | 3 | 4 | 24
1 | Console is inoperable | 2 | 3 | 5 | 30

## Elements
Physical | Software | Interop
serial | VxWorks | P-CSCF
ethernet | bootloader | S-CSCF
eth0 WANCOM0 | Acme OS | I-CSCF
eth1 WANCOM1 | SIP Stack | Access --> BGF
eth2 WANCOM2 | routing | Interconnect - BGF ????
| header manipulation | BGF - Media Server ???
NIU 0 | cli | BGF - PSTN ????
M00 | middle box control | Access --> GTM
M01 | monitor-SNMP | Interconnect -- GTM
HA
NIU 1 | Radius Auth
M10 | accounting
M11 | HDR -Collect
CPU
CAM

## TestCases
Test Case Name: | Upgrade -- interconnect | HMR -- NAT and strip 96 outbound on Interconnect | Inbound call test to Interconnect | DTMF IVR | Fail-Over Layer 1 interuption | Fail-Over Power Failure | Fail-over Layer 2 interuption | Config synchronization | Hold | Session Agent hunt distro-hunt | Media Time Out | Session Agent hunt distro-round robin | SBC HA link failure | Creation and restoration of a backup config | Radius Management Authentication | T-PIM interop | SNMP Polling | Console Port | Upgrade -- access | HMR -- access | Inbound call test to Access | DTMF IVR | Fail-Over Layer 1 interuption | Fail-Over Power Failure | Fail-over Layer 2 interuption | Config synchronization | Hold | Media Time Out | SBC HA link failure | Creation and restoration of a backup config | Forwarding | Call Waiting | DNS redundancy | HMR -- to and from to any | A calls B: on net | A calls B: PSTN | A calls B: off net through interconnect | A calls B: Emergency Call | encryption | A-SBC homes to a single P-CSCF | SBC to multiple P-CSCF's | CDR's | Radius Management Authentication | T-PIM interop | SNMP Polling | CALEA | Console Port | Upgrade -- BGF | Inbound call test through BGF | DTMF IVR trhough BGF | Fail-Over Layer 1 interuption--BGF | Fail-Over Power Failure -- BGF | Fail-over Layer 2 interuption -- BGF | Config synchronization --BGF | SBC HA link failure -- BGF | Creation and restoration of a backup config -- BGF | Radius Management Authentication -- BGF | T-PIM interop -- BGF | SNMP Polling -- BGF | H.248 Link BGF | Console Port
Test ID: | 200.01 | 200.02 | 200.03 | 200.04 | 200.05 | 200.06 | 200.07 | 200.08 | 200.09 | 200.10 | 200.11 | 200.12 | 200.13 | 200.14 | 200.15 | 200.16 | 200.17 | 200.18 | 100.01 | 100.02 | 100.03 | 100.04 | 100.05 | 100.06 | 100.07 | 100.08 | 100.09 | 100.10 | 100.11 | 100.12 | 100.13 | 100.14 | 100.15 | 100.16 | 100.17 | 100.18 | 100.19 | 100.20 | 100.21 | 100.22 | 100.23 | 100.24 | 100.25 | 100.26 | 100.27 | 100.28 | 100.29 | 300.01 | 300.02 | 300.03 | 300.04 | 300.05 | 300.06 | 300.07 | 300.08 | 300.09 | 300.10 | 300.11 | 300.12 | 300.13 | 200.14
Test Suite(s):
RPN
Hardware Req. | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair; BGCF; MGCF; MGW; MSS; 2 phones connected to PSTN | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as itnerconnect; P-CSCF; GTM; MGCF; MGW; MSS; 1 endpoint that can register to the IMS network; a lab T-PIM system; snif point on the management interface | SBC 4500 HA pair acting as Interconnect; P-CSCF; GTM; MGCF; MGW; MSS; 1 endpoint that can register to the IMS network; an endpoint capable of SNMP polling | SBC 4500 HA pair acting as interconnect; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network; Endpoint that will support a serial connection | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network; SBC pair with a different set of licenses than the Access pair | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network; a lab T-PIM system; snif point on the management interface | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network; an endpoint capable of SNMP polling | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network; Server to act as LI server; sniff point between LI server and SBC | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network; Endpoint that will support a serial connection | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network | SBC 4500 HA pair acting as itnerconnect; P-CSCF; GTM; MGCF; MGW; MSS; 1 endpoint that can register to the IMS network; a lab T-PIM system; snif point on the management interface | SBC 4500 HA pair acting as Interconnect; P-CSCF; GTM; MGCF; MGW; MSS; 1 endpoint that can register to the IMS network; an endpoint capable of SNMP polling | SBC 4500 HA pair acting as Interconnect; P-CSCF; GTM; MGCF; MGW; MSS; 1 endpoint that can register to the IMS network; sniff point between BGF, MSS, and MGW | SBC 4500 HA pair acting as Access; SBC 4500 HA pair acting as BGF; P-CSCF; GTM; MGCF; MGW; MSS; 3 endpoints that can register to the IMS network; Endpoint that will support a serial connection
Software Req. | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | SCX6.1.0 MR-6 patch 5; nnSCX610m6p5.gz | MCX1.0.0 Patch 4 ; SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0 MR-2; SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3 | SCX6.2.0M3
Duration: | 20 | 5 | 5 |  | 15 | 15 | 30 | 5 | 1 | 5 | 10 | 5 | 10 | 5 |  | 120 | 20 | 10 | 20 | 5 | 5 |  | 15 | 15 | 30 | 5 | 1 | 10 | 10 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 15 |  | 20 |  | 120 | 20 | 30 | 10 | 20 | 5 |  | 15 | 15 | 30 | 5 | 10 | 5 |  | 120 | 20 | 5 | 10
Effort: | 30 | 5 | 5 |  | 20 | 20 | 40 | 10 | 5 | 10 | 15 | 10 | 15 | 5 |  | 45 | 60 | 15 | 30 | 5 | 10 |  | 20 | 20 | 40 | 10 | 5 | 15 | 15 | 5 | 5 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 45 |  | 10 |  | 45 | 60 | 60 | 15 | 30 | 5 |  | 20 | 20 | 40 | 10 | 15 | 5 |  | 45 | 60 | 15 | 15
Setup: | Verify that all elements listed in hardware requirements are able to talk to each other; FTP nnSCX610m6p5.gz to /code/images in both SBC01 and SBC02; make a test call before executing test case | Verify that all elements listed in hardware requirements are able to talk to each other; Add the HMR rules as defined in MTP to the Session Agent (e.g. Ericsson, MGCF); save and activate the config | Verify that all elements listed in hardware requirements are able to talk to each other; This may require changes in the config to get all elements to work correctly. | Verify that all elements listed in hardware requirements are able to talk to each other; This may require changes in the config to get all elements to work correctly. |  |  |  | verify Outbound calls are working in the test bed |  | Create a session-agent group; verify two session-agents on the box and attach them to the created session-agent group; limit the first choice in the session-agent group to one max session. | Make sure that access to the next layer 2 hop is accessible | Create a session-agent group and set it to round robin; verify two session-agents on the box and attach them to the created session-agent group | You will need to have physical access to the SBC's to pull the HA interfaces, and a laptop connected to the boxes to verify that they each detect the failure |  | Modify SBC config to allow authentication from Lab Radius servers. Setup sniffing on the management interface. | Verify connectivity from the SBC to the T-PIM system and that the T-PIM system is ready to receive data from the SBC | Intergrate an SNMP capable endpoint into the test bed and point it at the management interface of the SBC; verify that the config will accept SNMP polling from the SNMP endpoint | Prepare endpoint that will connect via conosle | Verify that all elements listed in hardware requirements are able to talk to each other; FTP nnMCX100m1p1.gz to /code/images in both SBC01 and SBC02; make a test call before executing test case | Verify that all elements listed in hardware requirements are able to talk to each other; Add the HMR rules as defined in MTP to the Session Agent (e.g. Ericsson, MGCF); save and activate the config | Verify that all elements listed in hardware requirements are able to talk to each other; This may require changes in the config to get all elements to work correctly. | Verify that all elements listed in hardware requirements are able to talk to each other; This may require changes in the config to get all elements to work correctly. |  |  |  | verify Outbound calls are working in the test bed |  | Make sure that access to the next layer 2 hop is accessible | You will need to have physical access to the SBC's to pull the HA interfaces, and a laptop connected to the boxes to verify that they each detect the failure |  |  |  |  | Changed the HMR rule from matching IP's to matching any string in NAT_IP sip manipluation. Turn on 'notify sipd debug' and rotate the logs. |  |  |  |  | Setup encrytption on the access SBC (IPSec or TLS); setup a sniff point to see the traffic between UE and SBC; users A, B, and C are all registered to the call server | Setup of 3 P-CSCF instances on the core side of the A-SBC so that it has multiple paths to choose from; Resolution for incoming invites should be provided by a system like GTM, providing DNS resolution; Setup sniffing on the access and core sides of the SBC | Create a backup config on the different SBC's with a different set of licenses but the same configuration and transfer the file over to the SBC's acting as Access in the test bed | Turn on the accounting features in the Access SBC's | Modify SBC config to allow authentication from Lab Radius servers. Setup sniffing on the management interface. | Verify connectivity from the SBC to the T-PIM system and that the T-PIM system is ready to receive data from the SBC | Intergrate an SNMP capable endpoint into the test bed and point it at the management interface of the SBC; verify that the config will accept SNMP polling from the SNMP endpoint | Intergrate LI server into the test bed and verify connectivity between SBC and LI server | Prepare endpoint that will connect via conosle | Verify that all elements listed in hardware requirements are able to talk to each other; FTP nnSCX620m3p6.xz to /code/images in both SBC01 and SBC02; make a test call before executing test case | Verify that all elements listed in hardware requirements are able to talk to each other; This may require changes in the config to get all elements to work correctly. | Verify that all elements listed in hardware requirements are able to talk to each other; This may require changes in the config to get all elements to work correctly. |  |  |  | verify Outbound calls are working in the test bed | You will need to have physical access to the SBC's to pull the HA interfaces, and a laptop connected to the boxes to verify that they each detect the failure |  | Modify SBC config to allow authentication from Lab Radius servers. Setup sniffing on the management interface. | Verify connectivity from the SBC to the T-PIM system and that the T-PIM system is ready to receive data from the SBC | Intergrate an SNMP capable endpoint into the test bed and point it at the management interface of the SBC/BGF; verify that the config will accept SNMP polling from the SNMP endpoint |  | Prepare endpoint that will connect via conosle
Teardown: | 200.01: none; 200.02: none; 200.03: none; 200.15: Remove Radius config from SBC; 200.16: turn off the collector service in the SBC; 200.17: Remove SNMP endpoint from the test bed; 100.01: none; 100.02: none; 100.03: none; 100.21: Remove encryption settings from access SBC; 100.22: remove 2 of the P-CSCF from the environment; 100.24: turn off the accounting features in the Access SBC; 100.25: Remove Radius config from SBC; 100.26: turn off the collector service in the SBC; 100.27: Remove SNMP endpoint from the test bed; 300.01: none; 300.02: none; 300.10: Remove Radius config from SBC; 300.11: turn off the collector service in the SBC; 300.12: Remove SNMP endpoint from the test bed
ID
1 | Setup an inbound/outbound call | turn on sip debug 'notify sipd debug' | Place Inbound call | Place a call to an IVR (conference bridge) | Stand up a call through the interconnect SBC and verify call stays up without quality impact through the following steps | Stand up a call through the interconnect SBC and verify call stays up without quality impact through the following steps | Stand up a call through the interconnect SBC and verify call stays up without quality impact through the following steps | log into active and inactive SBCs and run the command 'disply-current-config-version'; note the number | Place call | setup a call and verify inbound/outbound media | Setup call and verify two way audio | setup a call and verify inbound/outbound media | setup a call and verify inbound/outbound media is unaffected through the following steps | Make a backup configuration | Attempt to login via SSH to the SBC | Configure the SBC to start the collector (HDR) service and to push files to the T-PIM at intervals of 15 minutes | A calls PSTN, leave these calls up through the following steps | A calls B, leave these calls up through the following steps | Setup an inbound/outbound call | turn on sip debug 'notify sipd debug' and 'notify sipd rotate-logs' | Place Inbound call | Place Outbound to an IVR (conference bridge) | Stand up a call through the access SBC and verify call stays up without quality impact through the following steps | Stand up a call through the access SBC and verify call stays up without quality impact through the following steps | Stand up a call through the access SBC and verify call stays up without quality impact through the following steps | log into active and inactive SBCs and run the command 'disply-current-config-version'; note the number | Place call | Setup call and verify two way audio | setup a call and verify inbound/outbound media is unaffected through the following steps | Make a backup configuration | A calls B | A calls B and the exchange media | back up the config | A calls B | A calls B | A calls B | A calls B | A calls Emergency Services | A calls B | A, B, and C send registers to the Access side fo the SBC; note which end point is registered to which P-CSCF; note expires timer in the 200 to the Register | A calls B and maintain the call through the following steps | A call B and C call the PSTN | Attempt to login via SSH to the SBC | Configure the SBC to start the collector (HDR) service and to push files to the T-PIM at intervals of 15 minutes | A calls B and C calls PSTN, leave these calls up through the following steps | Provision SBC to gather LI info for A and pass to LI server | A calls B and C calls PSTN, leave these calls up through the following steps | Setup an inbound/outbound call | Place Inbound call | Place Outbound to an IVR (conference bridge) | Stand up a call through the SBC/BGF and verify call stays up without quality impact through the following steps | Stand up a call through the SBC/BGF and verify call stays up without quality impact through the following steps | Stand up a call through the SBC/BGF and verify call stays up without quality impact through the following steps | log into active and inactive SBCs and run the command 'disply-current-config-version'; note the number | setup a call and verify inbound/outbound media is unaffected through the following steps | Make a backup configuration | Attempt to login via SSH to the SBC/BGF | Configure the SBC to start the collector (HDR) service and to push files to the T-PIM at intervals of 15 minutes | A calls PSTN, leave these calls up through the following steps | Turn on sniffing; A calls B | A calls B and C calls PSTN, leave these calls up through the following steps
2 | log into iSBC 01 and run 'show health' to verify it is inactive, if it is active, run 'notify berpd force' | Place Outbound call | verify that B rings, answer the call, verify 2-way audio and terminate call | when prompted, provide DTMF tones to access a menu | Physicaly remove slot 0, port 0 from the active SBC | Turn off both power supplies on the active SBC | Change the vlan on the switch connecting the active SBC | make a change to the config | Place call on hold | Attempt to setup a different call through the same session group and use the 'sh sipd agents' to verify that the second session went to the second agent. | shutdown vlan to port carrying media | Attempt to setup a different call through the same session group and use the 'sh sipd agents' to verify that the second session went to the second agent. | Unplug WANCOM1 and verify that health score decrements by 8 points | ftp a copy of the backup to a PC | use NT authentication to authenticate, verify that SBC contacted Radius in the capture. | Make random inbound/outbound calls both net-net and net-pstn | Poll the SBC management interface with apCombinedStatsCurrentActiveSessionsInbound (1.3.6.1.4.1.9148.3.2.1.2.1.1.4) and apCombinedStatsCurrentActiveSessionsOutbound (1.3.6.1.4.1.9148.3.2.1.2.1.1.6) and verify that the data returned reflects the current number of active session | connect to SBC via console and run 'show sessions' ; verify that the calls in step 1 appear | log into aSBC 01 and run 'show health' to verify it is inactive, if it is active, run 'notify berpd force' | Place Outbound call | verify that B rings, answer the call, verify 2-way audio and terminate call | when prompted, provide DTMF tones to access a menu | Physicaly remove the connection from slot 0, port 0 on the active SBC | Turn off both power supplies on the active SBC | Change the vlan on the switch connecting the active SBC | make a change to the config and save | Place call on hold | shutdown vlan to port carrying media | Unplug WANCOM1 and verify that health score decrements by 8 points | ftp a copy of the backup to a PC | A hits transfer and dials C | C calls A | change the primary and backup1 DNS to bogus Ips | Via FTP pull the logs off of the SBC | Verify 2 way audio | Verify 2 way audio | Verify 2 way audio | Once connected to emergency operator, explain that this is a test call | observe call setup with sniffing tool and verify that an encryption scheme is negotiated | A calls B and C calls PSTN; verify that the signalling is directed at the same P-CSCF as registration | Restore and active the backup config defined in the setup | Verify bi-diretional media for both calls | use NT authentication to authenticate, verify that SBC contacted Radius in the capture. | Make random inbound/outbound calls both net-net and net-pstn | Poll the SBC management interface with apCombinedStatsCurrentActiveSessionsInbound (1.3.6.1.4.1.9148.3.2.1.2.1.1.4) and apCombinedStatsCurrentActiveSessionsOutbound (1.3.6.1.4.1.9148.3.2.1.2.1.1.6) and verify that the data returned reflects the current number of active session | A calls B | connect to SBC via console and run 'show sessions' ; verify that the calls in step 1 appear | log into SBC 01 and run 'show health' to verify it is inactive, if it is active, run 'notify berpd force' | verify that B rings, answer the call, verify 2-way audio and terminate call | when prompted, provide DTMF tones to access a menu | Physicaly remove slot 0, port 0 from the active SBC | Turn off both power supplies on the active SBC/BGF | Change the vlan on the switch connecting the active SBC/BGF. | make a change to the config | Unplug WANCOM1 and verify that health score decrements by 8 points | ftp a copy of the backup to a PC | use NT authentication to authenticate, verify that SBC/BGF contacted Radius in the capture. | Make random inbound/outbound calls both net-net and net-pstn | Poll the SBC/BGF management interface with apCombinedStatsCurrentActiveSessionsInbound (1.3.6.1.4.1.9148.3.2.1.2.1.1.4) and apCombinedStatsCurrentActiveSessionsOutbound (1.3.6.1.4.1.9148.3.2.1.2.1.1.6) and verify that the data returned reflects the current number of active session | Verify two way audio and terminate B side; verify that A side is disconnected | connect to SBC/BGF via console and run 'show sessions' ; verify that the calls in step 1 appear
3 | run 'sh ver' and verify that the SBC is on SCX6.1.0 MR-1 Patch 6. | verify that B rings, answer the call, verify 2-way audio and terminate call |  | verify that the IVR accepts the digits correctly | Do a 'show health' on the failed SBC and note that the health has decremented and kicked off a fail over event | Do a 'show health' on the other SBC and verify that it is now active | logged into SBC, note time to fail over | verify that the current config version numbers increases by one | Take call off of hold |  | verify that the call is torn down after five minutes |  | issue a 'notify berpd force' | delete the backup configuration | Verify login attempt is successful and that permissions are the same for NT user as production | Using FTP, check that the SBC is creating the files correctly in the /ramdrv/collect/<group setting> directory | Remove cable from WANCOM01 and poll the SBC with apSysHealthScore (apSysMgmtGeneralObjects: 1.3.6.1.4.1.9148.3.2.1.1.3); verify that health score decrements by 8 points; Plug cable back into WANCOM01, poll again, and verify that health has returned to 100% | run 'show health' and if the SBC is active, run 'notify berpd force' so that the SBC is the inactive; run 'reboot' and verify that console connection isn't interupted during the boot process | run 'sh ver' and verify that the SBC is on MCX1.0.0 Patch 4 . | verify that B rings, answer the call, verify 2-way audio and terminate call |  | verify that the IVR accepts the digits correctly | Do a 'show health' on the failed SBC and note that the health has decremented and kicked off a fail over event | Do a 'show health' on the other SBC and verify that it is now active | logged into SBC, note time to fail over | verify that the current config version numbers increases by one | Take call off of hold | verify that the call is torn down after five minutes | issue a 'notify berpd force' | delete the backup configuration | B is transferred to C | A receives an indication of incoming call | attempt to make a call and verify that it fails | Verify that signaling into the access-lab interface is rewritten on egress into the core so that the from contained the local IP To contained the target IP | A terminates call | A terminates call | A terminates call | Record what information the Emergency operator has for A | A is connected to B and they exchange bi-directional media | Take down the P-CSCF to which all the end points are registered | Verify that the config loads correctly and that all features are defined correctly | after 15 minutes tear down calls | Verify login attempt is successful and that permissions are the same for NT user as production | Using FTP, check that the SBC is creating the files correctly in the /ramdrv/collect/<group setting> directory | Remove cable from WANCOM01 and poll the SBC with apSysHealthScore (apSysMgmtGeneralObjects: 1.3.6.1.4.1.9148.3.2.1.1.3); verify that health score decrements by 8 points; Plug cable back into WANCOM01, poll again, and verify that health has returned to 100% | verify from packet capture that SBC connects to LI server | run 'show health' and if the SBC is active, run 'notify berpd force' so that the SBC is the inactive; run 'reboot' and verify that console connection isn't interupted during the boot process | run 'sh ver' and verify that the SBC is on SCX6.2.0 MR-2 |  | verify that the IVR accepts the digits correctly | Do a 'show health' on the failed SBC/BGF and note that the health has decremented and kicked off a fail over event | Do a 'show health' on the other SBC and verify that it is now active | log into SBC/BGF, note time to fail over | verify that the current config version numbers increases by one | issue a 'notify berpd force' | delete the backup configuration | Verify login attempt is successful and that permissions are the same for NT user as production | Using FTP, check that the SBC is creating the files correctly in the /ramdrv/collect/<group setting> directory | Remove cable from WANCOM01 and poll the SBC with apSysHealthScore (apSysMgmtGeneralObjects: 1.3.6.1.4.1.9148.3.2.1.1.3); verify that health score decrements by 8 points; Plug cable back into WANCOM01, poll again, and verify that health has returned to 100% | review capture and verify H.248 signalling between BGF and MSS | run 'show health' and if the SBC/BGF is active, run 'notify berpd force' so that the SBC/BGF is the inactive; run 'reboot' and verify that console connection isn't interupted during the boot process
4 | change file name in bootparams to point to the /code/images/nnSCX610m6p5.gz | Pull sipmsg.log via FTP and examine the signaling to verify that the Core IP address has been replace with the Access IP throughout the messaging |  |  | Plug Slot 0, port 0 back in and verify that health is restored | Turn on both power supplies on the SBC that was turned off | Change the vlan back and verify that health returns to 100 | on the inactive SBC, verify that the current config version number has also increased by one. | terminate call |  |  |  | connect WANCOM1 and verify that 100 health is returned | setup a call and verify inbound/outbound media, releasing the call after media has been verified |  | With the sniff point, verify that the SBC is able to successfully connect via FTP and transmit the files | Remove cable from WANCOM02 and poll the SBC with apSysHealthScore (apSysMgmtGeneralObjects: 1.3.6.1.4.1.9148.3.2.1.1.3); verify that health score decrements by 9 points; Plug cable back into WANCOM02, poll again, and verify that health has returned to 100% |  | change file name in bootparams to point to the /code/images/nnSCX620m3.xz | Pull sipmsg.log via FTP and examine the signaling to verify that the Core IP address has been replace with the Access IP throughout the messaging |  |  | Plug Slot 0, port 0 back in and verify that health is restored | Turn on both power supplies on the SBC that was turned off | Change the vlan back and verify that health returns to 100 | on the inactive SBC, verify that the current config version number has also increased by one. | terminate call |  | connect WANCOM1 and verify that 100 health is returned | setup a call and verify inbound/outbound media, releasing the call after media has been verified | C and B exchange media and B terminates the call. | A answers C, putting B on hold, A and C exchange media | change backup1 to a real DNS server |  | Verify that B is disconnected from the call | Verify that B is disconnected from the call | Verify that B is disconnected from the call | Terminate the call | examine media stream between UE and A-SBC and verify that it is encrypted | When the registeration expires, verify that the End Points are able to re-register to a secondary P-CSCF |  | FTP CDR's off of the Access SBC |  | With the sniff point, verify that the SBC is able to successfully connect via FTP and transmit the files | Remove cable from WANCOM02 and poll the SBC with apSysHealthScore (apSysMgmtGeneralObjects: 1.3.6.1.4.1.9148.3.2.1.1.3); verify that health score decrements by 9 points; Plug cable back into WANCOM02, poll again, and verify that health has returned to 100% | Log into LI server and verify that the SBC has connected and pushed info about the call in step 2 |  | change file name in bootparams to point to the /code/images/nnSCX620m3p6.xz |  |  | Plug Slot 0, port 0 back in and verify that health is restored | Turn on both power supplies on the SBC/BGF that was turned off | Change the vlan back and verify that health returns to 100 | on the inactive SBC, verify that the current config version number has also increased by one. | connect WANCOM1 and verify that 100 health is returned | setup a call and verify inbound/outbound media, releasing the call after media has been verified |  | With the sniff point, verify that the SBC is able to successfully connect via FTP and transmit the files | Remove cable from WANCOM02 and poll the SBC with apSysHealthScore (apSysMgmtGeneralObjects: 1.3.6.1.4.1.9148.3.2.1.1.3); verify that health score decrements by 9 points; Plug cable back into WANCOM02, poll again, and verify that health has returned to 100%
5 | 200.01: reboot system, then log back in and run 'sh ver' and verify code is SCX6.1.0 MR-6 Patch 5; 200.05: Physicaly remove slot 0, port 0 from the SBC that has taken over active; 200.06: Do a 'show health' on the SBC that was turned back on and verify that it is now standby with full health; 200.07: change the vlan for the second SBC which is now active; 200.13: Unplug WANCOM2 and verify that health score decrements by 9 points; 200.14: Delete the HMR for the Ericsson MGCF and then save and activate the config; 200.16: After one hour of collection, review the files that have been pushed to T-PIM and that T-PIM was able to act on the data correctly; 200.17: Hang up call; 100.01: run 'sh ver' and verify that the SBC is on SCX6.2.0M3 .; 100.05: Physicaly remove the connection from slot 0, port 0 on the active SBC; 100.06: Do a 'show health' on the SBC that was turned back on and verify that it is now standby with full health; 100.07: change the vlan for the second SBC which is now active; 100.11: Unplug WANCOM2 and verify that health score decrements by 9 points; 100.12: Delete the HMR for the Ericsson MGCF and then save and activate the config; 100.14: A switches back to B, putting C on hold; 100.15: attempt to make a call and verify that it connects; 100.21: observe quality of the media and determine rough LQ and CQ; 100.22: A calls B and C calls PSTN; verify that the signalling is directed at the new P-CSCF; 100.24: verify through the CDR's that the time, duration, source, and destination of the calls were correctly recorded; 100.26: After one hour of collection, review the files that have been pushed to T-PIM and that T-PIM was able to act on the data correctly; 100.27: Hang up calls; 300.01: reboot system, then log back in and run 'sh ver' and verify code is SCX6.2.0 MR-3 Patch 6; 300.04: Physicaly remove slot 0, port 0 from the SBC/BGF that has taken over active; 300.05: Do a 'show health' on the SBC/BGF that was turned back on and verify that it is now standby with full health; 300.06: change the vlan for the second SBC/BGF which is now active; 300.08: Unplug WANCOM2 and verify that health score decrements by 9 points; 300.09: Delete all the steering pools on the BGF.; 300.11: After one hour of collection, review the files that have been pushed to T-PIM and that T-PIM was able to act on the data correctly; 300.12: Hang up call
6 | 200.01: run 'notify berpd force' to make iSBC 01 active; 200.05: Do a 'show health' on the new failed SBC and note that the health has decremented and kicked off a fail over event; 200.06: Turn off both power supplies on the active SBC; 200.07: logged into SBC, note time to fail over; 200.13: issue a 'notify berpd force'; 200.14: Make a call and verify that it no longer routes to the previous endpoint; 200.16: interrupt the connection between T-PIM and the SBC for one hour; 100.01: run 'notify berpd force' to make aSBC 01 active; 100.05: Do a 'show health' on the new failed SBC and note that the health has decremented and kicked off a fail over event; 100.06: Turn off both power supplies on the active SBC; 100.07: logged into SBC, note time to fail over; 100.11: issue a 'notify berpd force'; 100.12: Make a call and verify that it no longer routes to the previous endpoint; 100.14: B drops the call; 100.15: restore config from backup; 100.21: Leave call up; C calls PSTN; 100.26: interrupt the connection between T-PIM and the SBC for one hour; 300.01: run 'notify berpd force' to make SBC 01 active; 300.04: Do a 'show health' on the new failed SBC/BGF and note that the health has decremented and kicked off a fail over event; 300.05: Turn off both power supplies on the active SBC/SBC; 300.06: log into SBC/BGF, note time to fail over; 300.08: issue a 'notify berpd force'; 300.09: Make a call and verify that it no longer routes to the previous endpoint; 300.11: interrupt the connection between T-PIM and the SBC for one hour
7 | 200.01: log into iSBC 02 and run 'sh health' to verify 02 is inactive; 200.05: Plug Slot 0, port 0 back in and verify that health is restored; 200.06: Do a 'show health' on the other SBC and verify that it is now active; 200.07: Change the vlan back and verify that health returns to 100; 200.13: connect WANCOM2 and verify that 100 health is returned; 200.14: ftp the backup config back onto the primary SBC; 200.16: Restore the connection and verify that only the last 45 minutes worth of data was transmitted from the SBC to T-PIM; review data for problems.; 100.01: log into aSBC 02 and run 'sh health' to verify 02 is inactive; 100.05: Plug Slot 0, port 0 back in and verify that health is restored; 100.06: Do a 'show health' on the other SBC and verify that it is now active; 100.07: Change the vlan back and verify that health returns to 100; 100.11: connect WANCOM2 and verify that 100 health is returned; 100.12: ftp the backup config back onto the primary SBC; 100.14: C drops the call , and the call terminates correctly for A; 100.21: observe call setup with sniffing tool and verify that an encryption scheme is negotiated; 100.26: Restore the connection and verify that only the last 45 minutes worth of data was transmitted from the SBC to T-PIM; review data for problems.; 300.01: log into SBC 02 and run 'sh health' to verify 02 is inactive; 300.04: Plug Slot 0, port 0 back in and verify that health is restored; 300.05: Do a 'show health' on the other SBC/BGF and verify that it is now active; 300.06: Change the vlan back and verify that health returns to 100; 300.08: connect WANCOM2 and verify that 100 health is returned; 300.09: ftp the backup config back onto the primary SBC; 300.11: Restore the connection and verify that only the last 45 minutes worth of data was transmitted from the SBC to T-PIM; review data for problems.
8 | 200.01: change file name in bootparams to point to the /code/images/nnSCX610m6p5.gz; 200.06: Turn on both power supplies on the SBC that was turned off; 200.14: restore the backup configuration; 100.01: change file name in bootparams to point to the /code/images/nnMCX100m1p1.gz; 100.05: Terminate call on A side and verify that B side is disconnected; 100.06: Turn on both power supplies on the SBC that was turned off; 100.12: restore the backup configuration; 100.21: C is connected to PSTN and they exchange bi-directional media; 300.01: change file name in bootparams to point to the /code/images/nnSCX620m3p6.xz; 300.05: Turn on both power supplies on the SBC/SBC that was turned off; 300.09: restore the backup configuration
9 | 200.01: reboot system, then log back in and run 'sh ver' and verify code is SCX6.1.0 MR-6 Patch 5; 200.06: Do a 'show health' on the SBC that was turned back on and verify that it is now standby with full health; 200.14: setup a call and verify inbound/outbound media, releasing the call after media has been verified; 100.01: change file name in bootparams to point to the /code/images/nnSCX620m3.xz; 100.06: Do a 'show health' on the SBC that was turned back on and verify that it is now standby with full health; 100.12: setup a call and verify inbound/outbound media, releasing the call after media has been verified; 100.21: observe quality of the media and determine rough LQ and CQ; 300.01: reboot system, then log back in and run 'sh ver' and verify code is SCX6.2.0 MR-3 Patch 6; 300.05: Do a 'show health' on the SBC/BGF that was turned back on and verify that it is now standby with full health; 300.09: setup a call and verify inbound/outbound media, releasing the call after media has been verified
10 | 200.01: verify call stood up in step one is still active. Terminate the call on B-side and verify that A-side terminates call after timeout; 100.01: verify call stood up in step one is still active. Terminate the call on B-side and verify that A-side terminates call after timeout; 100.21: Terminat B and PSTN side and verify that A and C are disconnected.; 300.01: verify call stood up in step one is still active. Terminate the call on B-side and verify that A-side terminates call after timeout
Execution Summary | Worked as expected. | HMR rule worked as expected. | Inbound call worked | DTMF were accepted by the conference bridge | Un-plugging cable from slot M00 decrements the health to '20', and the standby becomes active. | Worked as expected. | Port shutdown (on the crcsnq01/02 routers) decrements the active SBC health to '0', and the standby becomes active. M00 and M01 interface on the SBC went down. During this status change/failover there is a blip (aduio loss) for a fraction of a second. | Worked as expected. | Looking into the SIP signaling, we found that the HOLD was being processed somewhere outside of the SBC and was transparent. | Worked as expected. | Worked as expected. VLAN 987 on brcsnq11/12 was shutdown which dropped the audio. The call was torn down after 5 minutes. | Worked as expected. | Worked as expected. | Worked as expected. | Worked as expected. Radius servers were deleted from the config which failed the NT authentication. The NT authentication worked after restoring the raidius server config. | Worked as expected. | Worked as expected. Only the .1.3.6.1.4.1.9148.3.2.1.2.1.1.4.5 OID for # of active sessions was verified. | Worked as expected. | Outbound call from a movial client to a LAB desk phone. | Will not test for this code release. | Inbound calls works for Movial client that are not behind the NAT. | Worked as expected. | Worked as expected. | The SCX6.2.0M3 code version supports either IPSec or TLS. We will be using TLS, and so this case failed intially as the device was configured with IPSec. The case passed after the IPSec config was removed. | Movial clientwithout NATing was used to stand up this call. | Worked as expected. | Worked as expected. | Call gets torn down after about 50 seconds since the RTP shutdown. | Worked as expected. | Worked as expected by placing outbound call. | Worked as expected. | This feature is not currently supported by IMS. | DNS redundancy worked as designed | Worked as expected. | Movial client A was behind the NAT, while Movial client B was not behind the NAT. Client A initiated call to client B succeeds. However call initiated by client B to client A fails. There seems to be some issue with Movial client behind NAT. | Worked as expected but the call was torn down after 10 minutes due to the client re-registeration. | Worked as expected. | Will not test for this code release. | Will not test for this code release. | Will not test for this code release. | TBD | Will not test on this code release | A backup of the current config was made. The A-SBC was made to point to bogus radius server IPs, which resulted in radius authentication failure. After that the backup was restored but the radius authentication did not work untill the A-SBC was rebooted. | Worked as expected. | The only OID that was verified was: .1.3.6.1.4.1.9148.3.2.1.2.1.1.6.2 | Will not test for this code release. | Worked as expected. | Worked as expected. | Worked as expected. | Worked as expected. | Worked as expected. Removing the cable from slot0 decrements the health score to 50. | Worked as expected. | Worked as expected. There was a brief audio loss for a fraction of a second when the port (gi7/19 on crcsnq) was shutdown. | Worked as expected. | Worked as expected. | Worked as expected. | Worked as expected. | Configuring a new push-receiver required a reboot to push the file using ftp. | The only OID that was verified was for CPU utilization: .1.3.6.1.4.1.9148.3.2.1.1.1.0. First-time SNMP configuration requires a reboot on both active and standby BGFs. |  | Worked as expected.
Status | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed. |  | Completed. | Completed. | Completed. | Conmpleted. | Completed | Completed. | Completed. | Completed. | Completed. | Completed | Completed |  | Completed | Completed | Completed | Completed | Completed | [5 empty] | Completed. | Completed. | Completed. |  | Completed. | Completed. | Completed. | Completed. | Completed. | Completed. | Completed. | Completed. | Completed. | Completed. | Completed. | Completed. | Completed. |  | Completed.
Tester | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Rahul | Walter, Rahul. |  | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. |  | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. | [5 empty] | Walter, Rahul. | Walter, Rahul. | Walter, Rahul. |  | Walter, Rahul. | Rahul. | Rahul. | Rahul. | Rahul. | Rahul. | Rahul. | Rahul. | Rahul. | Rahul. | Rahul. | Rahul. | Rahul. |  | Rahul.
Date Completed | 2010-08-27 | 2010-08-27 | 2010-08-27 | 2010-09-01 | 2010-09-01 | 2010-09-01 | 2010-09-01 | 2010-09-01 | 2010-09-01 | 2010-09-07 | 2010-09-02 | 2010-09-07 | 2010-09-07 | 2010-09-02 | 2010-09-02 | 2010-09-07 | 2010-09-07 | 2010-09-09 | 2010-07-27 |  | 2010-08-13 | 2010-08-06 | 2010-08-16 | 2010-08-16 |  | 2010-08-06 | 2010-08-16 | 2010-08-06 | 2010-08-16 | 2010-08-10 | 2010-08-16 |  | 2010-08-10 | 2010-08-10 | 2010-08-13 | 2010-08-10 | 2010-08-10 | [5 empty] | 2010-08-12 | 2010-08-12 | 2010-08-12 |  | 2010-08-16 | 2010-10-27 | 2010-10-27 | 2010-10-27 | 2010-11-03 | 2010-11-04 | 2010-11-04 | 2010-11-01 | 2010-11-04 | 2010-11-02 | 2010-11-01 | 2010-11-02 | 2010-11-02 |  | 11/142010
Effort | 20 | 30 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 20 | 10 | 20 | 5 | 10 | 10 | 60 | 10 | 5 | 120 |  | 20 | 30 | 10 | 20 |  | 30 | 10 | 20 | 10 | 20 | 90 |  | 20 | 20 | 20 | 15 | 90 | [5 empty] | 30 | 90 | 20 |  | 10 | 30 | 5 | 5 | 5 | 5 | 10 | 5 | 5 | 20 | 10 | 30 | 40 |  | 10
Duration | 20 | 10 | 5 | 10 | 20 | 20 | 15 | 10 | 10 | 10 | 20 | 10 | 20 | 20 | 20 | 60 | 20 | 20 | 20 |  | 10 | 20 | 20 | 60 |  | 20 | 10 | 20 | 20 | 10 | 10 |  | 10 | 10 | 10 | 15 | 20 | [5 empty] | 10 | 20 | 10 |  | 20 | 10 | 10 | 10 | 20 | 20 | 20 | 10 | 20 | 10 | 10 | 10 | 10 |  | 20
Result | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS |  | PASS | PASS | PASS | PASS | PASS | [5 empty] | PASS | PASS | PASS |  | PASS | PASS | IMS Failure | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | Not tested for this code release | PASS
final time est. in hours
duration
14.8333
effort
18
time completed in hours
duration
14.0833
effort
18.9167
est. for 100's
duration
5.8167
effort
8.1667
time completed for 100's
duration
5.75
effort
11.5833

## TestCaseCoverage
| SCX6.1.0 MR-6 | [17 empty] | MCX1.0.0 MR-1 Patch 1 | [28 empty] | SCX6.2.0 MR-2
Risks | 200.01 | 200.02 | 200.03 | 200.04 | 200.05 | 200.06 | 200.07 | 200.08 | 200.09 | 200.10 | 200.11 | 200.12 | 200.13 | 200.14 | 200.15 | 200.16 | 200.17 | 200.18 | 100.01 | 100.02 | 100.03 | 100.04 | 100.05 | 100.06 | 100.07 | 100.08 | 100.09 | 100.10 | 100.11 | 100.12 | 100.13 | 100.14 | 100.15 | 100.16 | 100.17 | 100.18 | 100.19 | 100.20 | 100.21 | 100.22 | 100.23 | 100.24 | 100.25 | 100.26 | 100.27 | 100.28 | 100.29 | 300.01 | 300.02 | 300.03 | 300.04 | 300.05 | 300.06 | 300.07 | 300.08 | 300.09 | 300.10 | 300.11 | 300.12 | 300.13 | 300.14
UE isn't able to place inbound/outbound calls net-net, net-pstn, net-comcast, net-sprint | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
UE doesn't get to emergency services | MCX1.0.0 MR-1 Patch 1 100.20: 2
Media not handled by SBC as expected (NAT traversal on Access/Interconnect) | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2
replication of data between SBC's | SCX6.1.0 MR-6 200.01: 2; SCX6.1.0 MR-6 200.05: 2; SCX6.1.0 MR-6 200.06: 2; SCX6.1.0 MR-6 200.07: 2; SCX6.1.0 MR-6 200.13: 2; MCX1.0.0 MR-1 Patch 1 100.01: 2; MCX1.0.0 MR-1 Patch 1 100.05: 2; MCX1.0.0 MR-1 Patch 1 100.06: 2; MCX1.0.0 MR-1 Patch 1 100.07: 2; MCX1.0.0 MR-1 Patch 1 100.11: 2; MCX1.0.0 MR-1 Patch 1 100.23: 1; SCX6.2.0 MR-2 300.01: 2; SCX6.2.0 MR-2 300.04: 2; SCX6.2.0 MR-2 300.05: 2; SCX6.2.0 MR-2 300.06: 2; SCX6.2.0 MR-2 300.08: 2
replication of config between SBC's | SCX6.1.0 MR-6 200.01: 1; SCX6.1.0 MR-6 200.05: 1; SCX6.1.0 MR-6 200.06: 1; SCX6.1.0 MR-6 200.07: 1; SCX6.1.0 MR-6 200.08: 2; SCX6.1.0 MR-6 200.13: 1; MCX1.0.0 MR-1 Patch 1 100.01: 1; MCX1.0.0 MR-1 Patch 1 100.05: 1; MCX1.0.0 MR-1 Patch 1 100.06: 1; MCX1.0.0 MR-1 Patch 1 100.07: 1; MCX1.0.0 MR-1 Patch 1 100.08: 2; MCX1.0.0 MR-1 Patch 1 100.11: 1; MCX1.0.0 MR-1 Patch 1 100.23: 1; SCX6.2.0 MR-2 300.01: 1; SCX6.2.0 MR-2 300.04: 1; SCX6.2.0 MR-2 300.05: 1; SCX6.2.0 MR-2 300.06: 1; SCX6.2.0 MR-2 300.07: 2; SCX6.2.0 MR-2 300.08: 1
backed up configs can't be used | SCX6.1.0 MR-6 200.14: 2; SCX6.1.0 MR-6 200.15: 2; MCX1.0.0 MR-1 Patch 1 100.12: 2; MCX1.0.0 MR-1 Patch 1 100.23: 2; MCX1.0.0 MR-1 Patch 1 100.26: 2; SCX6.2.0 MR-2 300.09: 2; SCX6.2.0 MR-2 300.10: 2
SIP routing doesn't route the calls | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 2 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | [8 empty] | 1 | 1 | 1 | 1 |  |  | 2 |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 2 |  | 2
TLS or Ipsec doesn't allow setup for signalling | MCX1.0.0 MR-1 Patch 1 100.21: 2
SBC is unable to bind a given UE to a given Porxy through the course of a registration | MCX1.0.0 MR-1 Patch 1 100.22: 2
virtual IP's don't move over in a fail over | SCX6.1.0 MR-6 200.01: 2; SCX6.1.0 MR-6 200.05: 2; SCX6.1.0 MR-6 200.06: 2; SCX6.1.0 MR-6 200.07: 2; SCX6.1.0 MR-6 200.13: 2; MCX1.0.0 MR-1 Patch 1 100.01: 2; MCX1.0.0 MR-1 Patch 1 100.05: 2; MCX1.0.0 MR-1 Patch 1 100.06: 2; MCX1.0.0 MR-1 Patch 1 100.07: 2; MCX1.0.0 MR-1 Patch 1 100.11: 2; SCX6.2.0 MR-2 300.01: 2; SCX6.2.0 MR-2 300.04: 2; SCX6.2.0 MR-2 300.05: 2; SCX6.2.0 MR-2 300.06: 2; SCX6.2.0 MR-2 300.08: 2
SBC and P-CSCF can't distinguish signalling between multiple end points | SCX6.1.0 MR-6 200.15: 2; SCX6.1.0 MR-6 200.17: 2; MCX1.0.0 MR-1 Patch 1 100.21: 2; MCX1.0.0 MR-1 Patch 1 100.24: 2; MCX1.0.0 MR-1 Patch 1 100.26: 2; MCX1.0.0 MR-1 Patch 1 100.28: 2; SCX6.2.0 MR-2 300.10: 2; SCX6.2.0 MR-2 300.12: 2
BGF is not provided destination for incoming media | [14 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | [9 empty] | 2 | 2 | 2 | 2 | 2
DTMF isn't handled correctly | SCX6.1.0 MR-6 200.04: 2; MCX1.0.0 MR-1 Patch 1 100.04: 2; SCX6.2.0 MR-2 300.03: 2
SBC is unable to resolve hostname to IP | MCX1.0.0 MR-1 Patch 1 100.15: 2; MCX1.0.0 MR-1 Patch 1 100.22: 2; MCX1.0.0 MR-1 Patch 1 100.23: 2
A remote copy of a backup config does not work when loaded | SCX6.1.0 MR-6 200.14: 2; MCX1.0.0 MR-1 Patch 1 100.12: 2; MCX1.0.0 MR-1 Patch 1 100.23: 2; SCX6.2.0 MR-2 300.09: 2
unlicensed feature in config (saved on one SBC and moved to a second SBC with different licenses | MCX1.0.0 MR-1 Patch 1 100.23: 2
CDR's don't report correctly (? Radius vs. FTP Push) | MCX1.0.0 MR-1 Patch 1 100.24: 2
SBC doesn't terminate call after UE loses connectivity | SCX6.1.0 MR-6 200.11: 2; MCX1.0.0 MR-1 Patch 1 100.10: 2
Ethernet port fails at layer 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | [10 empty] | 2 |  |  | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2
HA event doesn't handle IP's Correctly | SCX6.1.0 MR-6 200.01: 2; SCX6.1.0 MR-6 200.05: 2; SCX6.1.0 MR-6 200.06: 2; SCX6.1.0 MR-6 200.07: 2; SCX6.1.0 MR-6 200.13: 2; MCX1.0.0 MR-1 Patch 1 100.01: 2; MCX1.0.0 MR-1 Patch 1 100.05: 2; MCX1.0.0 MR-1 Patch 1 100.06: 2; MCX1.0.0 MR-1 Patch 1 100.07: 2; MCX1.0.0 MR-1 Patch 1 100.11: 2; SCX6.2.0 MR-2 300.01: 2; SCX6.2.0 MR-2 300.04: 2; SCX6.2.0 MR-2 300.05: 2; SCX6.2.0 MR-2 300.06: 2; SCX6.2.0 MR-2 300.08: 2
SIP message doesn't arrive in the expected formate (HMR) | SCX6.1.0 MR-6 200.01: 1; SCX6.1.0 MR-6 200.02: 2; SCX6.1.0 MR-6 200.04: 1; SCX6.1.0 MR-6 200.05: 1; SCX6.1.0 MR-6 200.06: 1; SCX6.1.0 MR-6 200.10: 1; SCX6.1.0 MR-6 200.11: 1; SCX6.1.0 MR-6 200.12: 1; SCX6.1.0 MR-6 200.13: 1; SCX6.1.0 MR-6 200.14: 1; MCX1.0.0 MR-1 Patch 1 100.01: 1; MCX1.0.0 MR-1 Patch 1 100.02: 2; MCX1.0.0 MR-1 Patch 1 100.04: 1; MCX1.0.0 MR-1 Patch 1 100.05: 1; MCX1.0.0 MR-1 Patch 1 100.06: 1; MCX1.0.0 MR-1 Patch 1 100.10: 1; MCX1.0.0 MR-1 Patch 1 100.11: 1; MCX1.0.0 MR-1 Patch 1 100.12: 1; MCX1.0.0 MR-1 Patch 1 100.16: 2; SCX6.2.0 MR-2 300.01: 1; SCX6.2.0 MR-2 300.03: 1; SCX6.2.0 MR-2 300.04: 1; SCX6.2.0 MR-2 300.05: 1; SCX6.2.0 MR-2 300.08: 1; SCX6.2.0 MR-2 300.09: 1
Radius Auth doesn't allow authentication | MCX1.0.0 MR-1 Patch 1 100.25: 2
HDR doesn't interact with T-PIM or provides incorrect/unusable data | SCX6.1.0 MR-6 200.15: 2; MCX1.0.0 MR-1 Patch 1 100.26: 2; SCX6.2.0 MR-2 300.10: 2
Interruption of the HDR causes unexceptable loss of data | SCX6.1.0 MR-6 200.15: 2; MCX1.0.0 MR-1 Patch 1 100.26: 2; SCX6.2.0 MR-2 300.10: 2
SBC doesn't handle switched services (CW, hold, 3-way, forwarding) | SCX6.1.0 MR-6 200.09: 2; MCX1.0.0 MR-1 Patch 1 100.09: 2; MCX1.0.0 MR-1 Patch 1 100.13: 2; MCX1.0.0 MR-1 Patch 1 100.14: 2
SNMP polls return bad data | SCX6.1.0 MR-6 200.16: 2; MCX1.0.0 MR-1 Patch 1 100.27: 2; SCX6.2.0 MR-2 300.11: 2
Collection push errors | SCX6.1.0 MR-6 200.15: 2; MCX1.0.0 MR-1 Patch 1 100.26: 2; SCX6.2.0 MR-2 300.10: 2
CALEA doesn't interact with Star Gate correctly | SCX6.1.0 MR-6 200.17: 2; MCX1.0.0 MR-1 Patch 1 100.28: 2; SCX6.2.0 MR-2 300.12: 2
Headers that describe priv network are passed to UE/Peers | SCX6.1.0 MR-6 200.02: 2; MCX1.0.0 MR-1 Patch 1 100.02: 2
Call stood up fails during a config change/upgrade | SCX6.1.0 MR-6 200.01: 2; SCX6.1.0 MR-6 200.05: 2; SCX6.1.0 MR-6 200.06: 2; SCX6.1.0 MR-6 200.07: 2; MCX1.0.0 MR-1 Patch 1 100.01: 2; MCX1.0.0 MR-1 Patch 1 100.05: 2; MCX1.0.0 MR-1 Patch 1 100.06: 2; MCX1.0.0 MR-1 Patch 1 100.07: 2; SCX6.2.0 MR-2 300.01: 2; SCX6.2.0 MR-2 300.04: 2; SCX6.2.0 MR-2 300.05: 2; SCX6.2.0 MR-2 300.06: 2
Console is inoperable | SCX6.1.0 MR-6 200.18: 2; MCX1.0.0 MR-1 Patch 1 100.29: 2; SCX6.2.0 MR-2 300.14: 2

## Glossary
SBC | Session Border Control. This is the system under test
LQ | Listening Quality. Part of the R-Factor which determines the quality of sound in the transmission. A scratchy connection or one impacted by sound artifacts would have a low LQ while a high fidelity sound experience would give a high score.
CQ | Conversation Quality. Inidcates how easy it is for the parties to talk to each other and is usually ruled by delay. A high delay causes the parties to talk over each other. In extreme cases, parties have to indicate that they are finished talking in order to allow the other participants to respond. This is usual achieved by saying "over" at the end of a message. I high CQ indicates no delay between a party speaking and his message arriving at the hearer.
SUT | System Under Test. This is a generic way to talk about the subject of test cases
CDR | Call Detail Reports. The CDR's that are supported for the Acme product are explained in the Accounting Guide.

## IMS Core Issues
Issue # | Description | owner | Last Update
1 | End Point recieves a 403 when attempting to re-register | Puneet; | 2010-08-06
2 | calling the same number produces four different results: success, a 404, a 480, and the call being terminated with a BYE after .5 seconds. | Puneet | 2010-08-06
3 | Inbound calls aren't working | Arnold | ***
4 | Hold doesn't work | unknown | ***
5 | Transfers and forwarding doesn't work | unknown | ***